## Sheet1
SCHEDULE OF WORK
EXTENSION AND ALTERATIONS
MENSWEAR
for
2010-02-01
File ref: 2901
PROJECT: | EXTENSION AND ALTERATIONS, MENSWEAR,
INDEX
PRELIMINARIES
SCHEDULE OF WORK
FINAL SUMMARY
FORM OF TENDER
APPENDICES:
A – Demolitions and Alterations Plan
B – Substructures Plan
C – Roof Plan
D – Ceiling Plan
E – Site Works Plan
PRELIMINARIES
SCHEDULE OF WORK
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
DEMOLITIONS AND ALTERATIONS
Preparation
A | Locate; isolate and make safe all services; remove any services and other fittings; set aside as required for reuse; remove unwanted from site; alter and adapt to maintain services, including any temporarysupplies; protect and reinstate services to suit the proposed works. Make good all work disturbed | 1 | ITEM | 0 | 1577.5
B | Remove trees; hedges; and other landscaping as necessary. Grub up roots – avoiding any damage to buildings and foundations. Backfill voids as necessary. Remove trees and arisings and debris from site. | 1 | ITEM | 0 | 1062.5
C | Remove walls, fencing and gates in the area of the works and access into the site; (including brick boundary walls). Set aside useable material for reuse. Remove debris from site. | 1 | ITEM | 0 | 675
D | Remove pavings, set aside for reuse; remove debris from site. | 1 | ITEM | 0 | 300
Composite Items
Include for temporary supports needle propping and supporting; demolition; alteration; cutting and forming openings; (or combination of cutting and building up); forming and inserting beams or lintels, jambs, cills and the like. Grub up foundations and prepare for new works. Make safe and seal services. Set aside materials suitable for reuse in the works and remove remainder from site. Make good all work disturbed to match adjacent finishes. ----------------------------------------------------------------------------
E | Walls, and associated fixtures; fittings; and finishes to area hatched green on plan Appendix A. | 1 | ITEM | 0 | 887.5
F | Roof finishes to area edged orange on plan Appendix A | 1 | ITEM | 0 | 1050
G | Roof structure to area edged orange on plan Appendix A (provisional). | 1 | ITEM | 0 | 825
H | Remove door and screen from existing store form and fill in opening including window to new kitchen. | 1 | ITEM | 0 | 600
I | Insert supporting beam 305 x 127 x 48 UB (B5) on precast concrete padstones with rag bolts (4 No) through bottom flange | 1 | ITEM |  | 937.5
J | Include for encasing in two layers 12.5 plasterboard and skim coat plaster on metal stud framing. | 1 | ITEM |  | 187.5
_______
|  |  |  | To Collection £ | 8102.5
_______
2/1.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
A | Fill in opening to existing store with partition and door to form new kitchen. | 1 | ITEM | 0 | 789.096
B | Remove fittings and sanitaryware comprising:-
- Changing cubicles
- Sink unit, boiler and services
- WC pan
| - Counter | 1 | ITEM | 0 | 1980
C | Form opening at first floor including incorporating door for future access to flat including removing any fittings within first floor to accommodate opening. | 1 | ITEM | 0 | 637.5
D | Include for any other items shown on the drawings or properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
Collection
|  |  | 2/1. |  | 8102.5
|  |  | 2/2. |  | 3406.596
_______
DEMOLITIONS
|  |  |  | AND £ | 11509.096
|  |  |  | ALTERATIONS | _______
TO SUMMARY
2/2.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
SUBSTRUCTURES
Preparation
A | Include for excavating trial holes (include 2 No Provisional) to establish further detail of any existing foundations. | 1 | ITEM | 0 | 400
B | Clear site in preparation for the works, remove materials from site. | 1 | ITEM | 0 | 375
Excavation and Earthworks
C | Excavate to reduce levels as required; prepare surfaces, treat with weed killer. | 1 | ITEM | 0 | 875
D | Excavate for foundation trenches to external and internal walls as indicated on drawings including preparing surfaces. | 1 | ITEM | 0 | 800
Disposal
E | Dispose of unwanted excavated material by removal from site. | 1 | ITEM | 0 | 800
site.
Composite Items
Concrete (grade C25) strip foundations and brick/block walls up to and including Hyload damp-proof course. Blockwork below DPC to be dense blockwork (7N/mm2) in cement mortar ----------------------------------------------------------------------------
F | To external and internal walls (adjust to suit width of internal walls). | 1 | ITEM | 0 | 5556.25
Sundries
G | Include for telescopic air vents and air bricks below dpc as shown. | 1 | ITEM | 0 | 175
H | Cut tooth and bond foundation blockwork to corner of existing walls. | 1 | ITEM | 0 | 225
_______
|  |  |  | To Collection £ | 9206.25
_______
2/3.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
New Floors
A | Beamshield Plus precast concrete beam and block floor to CP110 to area hatched blue on plan Appendix B. Include for manufacturer’s calculations to comply with Building Regulations | 1 | ITEM | 0 | 12350
B | Damp proof membrane/Radon barrier to be 300 mirror membrane with welted laps and lap with horizontal dpc. Including Hyload cavity tray lapped with dpc and dressed behind breather membrane of timber frame. | 1 | ITEM | 0 | 1087.5
C | Weep holes and plastic vents above cavity tray. | 1 | ITEM | 0 | 125
Precast Concrete Lintels
D | To be provided over drains and services where they pass through new walls. Maintain 50 mm air gap around pipe and each side of wall to be masked. | 1 | ITEM | 0 | 100
E | Include for any other items shown on the drawings or properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_______
|  |  |  | To Collection £ | 13662.5
_______
Collection
|  |  | 2/3. |  | 9206.25
|  |  | 2/4. |  | 13662.5
|  |  |  | SUBSTRUCTURES £ | 22868.75
TO SUMMARY
2/4.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
EXTERNAL WALLS
Preparation and Re-building
A | Prepare existing walls, including external and internal finishes following demolitions. Re-building, cutting, toothing and bonding; remove debris from site and make good to all vertical corners and junctions. | 1 | ITEM | 0 | 862.5
B | Include the provision sum of £750 for strapping, tying in, or supporting walls as engineers details. | 1 | ITEM | 0 | 750
New Walls
C | Walls of facing bricks to match existing for size, colour, texture, bond and joint, including fixing wall ties to timber frame (supplied by timber frame manufacturer). | 1 | ITEM | 0 | 29300
D | Extra for cutting toothing and bending walls to existing. | 1 | ITEM | 0 | 750
E | Include the sum of £……… for timber frame walls by specialist contractor. | 1 | ITEM | 0 | 25000 | Client supplied Provisional sum
F | Include for liaising with timber frame contractor for setting out; checking dimensions; including for profit and general attendance. | 1 | ITEM | 0 | 4050
G | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
|  |  | EXTERNAL |  | _______
|  |  | WALLS £ |  | 60712.5
|  |  | TO SUMMARY |  | _______
2/5.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
ROOFS
Preparation and Alteration
Note: The roof structure, including flat roof; firrings; parapets; pitched roof structure to eaves; boarding to flat roof and upstands will be part of the timber frame package. (See 2/5 – Items E & F)
Remove; prepare for new; and remove debris from site '------------------------------------------------------------------
A | Roof structure to area edged orange on plan Appendix A | 1 | ITEM | 0 | 1512.5
B | Roof finishes to area edged orange on plan Appendix A. | 1 | ITEM | 0 | 2875
Metalwork
C | Include the provision sum of £500 for strapping of roofs. | 1 | ITEM | 0 | 500
Roof Finishes
D | Plain clay tiles to match existing on 50 x 25 treated battens on Tyvek breathable felt to pitched roofs at eaves as edged green on plan Appendix C | 1 | ITEM | 0 | 4650
Ridges
E | Clay ridge tiles, mono ridge, bedding and pointing in mortar to parapet pitched eaves ridges. | 1 | ITEM | 0 | 1425
Eaves
F | Double course of tiles at eaves including boarding above exposed rafter ends in T&G and beaded boarding to close off eaves. | 1 | ITEM | 0 | 862.5
Verges
G | Natural slate undercloak and alternate tile and half at verges, pointing in lime mortar at change of height of parapet and at staircase opening through pitched eaves. | 1 | ITEM | 0 | 537.5
_______
|  |  |  | To Collection £ | 12362.5
2/6.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
Hips
A | Clay arris hips to match tiles. | 1 | ITEM | 0 | 390
B | Extra for hip irons. | 1 | ITEM | 0 | 52.5
Flashings and Abutments
C | Code 4 lead soakers to tiles at abutments. | 1 | ITEM | 0 | 212.5
D | Code 5 lead flashings at abutments and interface with existing roof to kitchen including cutting back and forming layer boards and all flashings, refixing tiles and the like. | 1 | ITEM | 0 | 711.25
E | Cutting into existing walls at abutments to form cavity tray, Code 5 flashings and weep holes to sloping; horizontal; and vertical abutments of roofs to existing wall. | 1 | ITEM | 0 | 438.75
Roof Decking/Finishes
F | Polyroof finish to flat roof area and parapet upstands including all angles; dressing into gutters and outlets; and the like in accordance with manufacturer’s instructions. As edged orange on plan Appendix C. | 1 | ITEM | 0 | 35825
G | Promenade decking tiles Eurodeck Regency Aged Terracotta (Tel: 01963 33940) fixed in accordance with manufacturer’s instructions on plastic spacers to flat roof area (provisional). | 70 | M2 | 0 | 2625
Insulation
H | Fix only roof insulation (provided by timber frame supplier). | 1 | ITEM | 0 | 575
Sundries
I | Include for through ventilation at eaves. | 1 | ITEM | 0 | 781.25
Rainwater Disposal
J | Balcony roof outlet and pipe from flat roof through sloping eaves including trimming to joists as required; connection to rainwater pipes. | 1 | ITEM | 0 | 288
_______
|  |  |  | To Collection £ | 41899.25
2/7.
Collection
|  |  | 2/6. |  | 12362.5
|  |  | 2/7. |  | 41899.25
_______
|  |  | ROOFS £ |  | 54261.75
TO SUMMARY
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
STAIRS
Composite Item
A | Foundations for stair comprising excavation; remove material from site; concrete foundation 1500 x 600 x 600 trowel finish to top; chamfered edges; setting in and including 4 No 200 x 20 rag bolts to take stair base plates. | 1 | ITEM | 0 | 860
Purpose-made steel
B | Include the sum of £……… for steel staircase by specialist contractor. | 1 | ITEM | 0 | 4000 | Client supplied Provisional sum
C | Include for profit and attendance. | 1 | ITEM | 0 | 600
D | Include for liaising with specialist contractor to establish dimensions; include for unloading and assistance with fixing. | 1 | ITEM | 0 | 312.5
Insitu Finishes
E | Eurodeck (01963 33940) GRP non-slip treads and nosings to stairs and landing. | 1 | ITEM | 0 | 375
______
|  |  | STAIRS TO £ |  | 6147.5
SUMMARY
WINDOWS AND EXTERNAL DOORS
Standard or Purpose-Made Joinery
Premdor, Standard Joinery --------------------------------
F | Windows Design 24 Metric 626 x 1050 non bar side hung; factory glazed (2 No) | 2 | ITEM | 0 | 208.8
factory glazed (2 No)
______
|  |  | To Collection |  | 208.8
2/8.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
Purpose-made softwood treated with pressure impregnated softwood after manufacture -----------------------------------------------------------------------
A | Pair of double doors and frame to rear elevation. Framed, ledged and braced and T&G beaded boarding; including rebated meeting styles; draft proofing; two pairs 100 mm stainless steel hinges to each leaf; emergency panic bolt with key operations from outside; hold open stays; disabled access threshold and all fixings. | 1 | ITEM | 0 | 452.76
Surrounds to Windows and Doors
Heads
B | Fix only lintels (lintels supplied by timber frame manufacturer). Include for dpc and closer. | 1 | ITEM | 0 | 250
Jambs
C | Form jambs including dpc and cavity closers. | 1 | ITEM | 0 | 250
Cills
D | Form cills including dpc and cavity closers. | 1 | ITEM | 0 | 250
E | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_______
|  |  |  | To Collection £ | 1202.76
_______
Collection
|  |  | 2/8. |  | 208.8
|  |  | 2/9. |  | 1202.76
_________
|  |  |  | WINDOWS AND £ | 1411.56
|  |  |  | EXTERNAL DOORS | _________
TO SUMMARY
2/9.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
INTERNAL WALLS
Note:
The internal walls are part of the timber frame package.
A | Fix only sound deadening insulation in internal walls (insulation supplied by timber frame contractor). | 1 | ITEM | 0 | 375
B | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_________
|  |  |  | INTERNAL WALLS £ | 375
|  |  |  | TO SUMMARY | _________
2/10.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
INTERNAL DOORS
Standard Softwood Joinery
Door linings 38 mm thick to suit wall thickness; 32 x 13 stops; Premdor, Durador doors; architraves; ironmongery to match existing. -----------------------------------------------------------------------------
A | 926 x 2049 x 40 with disabled unisex sign symbol. | 1 | ITEM | 0 | 257.304
B | 826 x 2040 x 40 fire door FD30S with vision panel to Kitchen | 1 | ITEM | 0 | 306
C | 926 x 2040 x 40 to Rear Lobby | 1 | ITEM | 0 | 257.304
D | Pair 626 x 2040 x 40 to Store | 1 | ITEM | 0 | 220.8
E | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_________
|  |  |  | INTERNAL DOORS £ | 1041.408
TO SUMMARY
2/11.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
WALL FINISHES
Alterations and Preparations
A | Remove linings, fixtures and fittings; remove from site. | 1 | ITEM | 0 | 187.5 | P,sum
B | Cut out defective or inappropriate finishes at junctions of new and old and make good. | 1 | ITEM | 0 | 175 | Includes approx. 10m2
Insitu Finishes
Plasterboard 15 mm thick and 3 mm skim coat finish including angles and forming corners on polythene vapour control layer ---------------------------------------------------------------------------
C | Unisex WC; Rear Lobby; and Store | 27 | M2 | 0 | 1168.344
Board Finishes
Plywood linings 12 mm screw fixed at 150 centres to the timber frame on polythene vapour control layer ----------------------------------------------------------------------
D | All walls to new proposed Retail Area | 27 | M2 | 0 | 429.3
Tile, Sheet and Insitu Finishes
Include the sum of £50/m2 for client’s choice of glazed tiles to walls and reveals. Add for PVC angle beads to match. Add for profit on tiles for waterproof adhesive; and waterproof grout; and fix to the following areas:-----------------------------------------------------------------------
E | Walls 2100 high to Unisex WC | 13 | M2 | 0 | 1387.75
F | 450 high around worktops, including returns to Kitchen | 2 | M2 | 0 | 201.5
G | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
|  |  |  | WALL FINISHES £ | 3549.394
|  |  |  | TO SUMMARY | _________
2/12.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
FLOOR FINISHES
Preparation and Alteration
A | Remove all existing floor finishes; make good; adjusting levels to constant surface; remove debris from site. Prepare floor areas to receive finishes | 1 | ITEM | 0 | 2173.164
Insitu Finishes
B | 75 mm sand and cement screed to beam and block floors. | 80 | M2 | 0 | 1800
Tile, Sheet and Insitu Finishes
C | Altro High Performance safety flooring, and 100 mm coved skirting to Kitchen and Unisex WC. | 1 | ITEM | 0 | 995.112
D | Amtico, Spacia Warm Maple fixed in accordance with manufacturer’s instructions to new floor area (excluding Kitchen and Unisex WC) | 1 | ITEM | 0 | 5238.672
E | Grime Buster 7700 Heavy Contract Dirt Barrier mat at entrance to shop as existing including hardwood edging surround tapered to meet other floor finishes | 1 | ITEM | 0 | 142.032
Skirtings
F | Wrought softwood skirtings 150 x 25 chamfered top edge to Rear Lobby and Store | 16 | L,m | 0 | 138.24
Sundries
G | Silicone seal to all edges and angles | 1 | ITEM | 0 | 125.556
H | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | 2064.216 | Includes for Latex screed & DPM to all areas
_________
|  |  |  | FLOOR FINISHES £ | 12676.992
|  |  | TO SUMMARY |  | _________
2/13.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
CEILING FINISHES
Preparation and Alteration
A | Remove suspended ceilings from area hatched green on plan Appendix A. Remove debris from site. | 200 | M2 | 0 | 979.2
Board and Insitu Finishes
B | Plasterboard 15 mm thick, foil backed and skim coat finishes on polythene vapour control layer to Kitchen; Unisex WC; Lobby; and Store. | 29 | M2 | 0 | 806.664
Proprietary Ceilings
C | Suspended ceiling, 600 x 600 tile to match existing in lay in grid to area hatched orange on plan Appendix D. | 110 | M2 | 0 | 2327.16
Woodwork
Wrought Softwood
-----------------------
D | 50 x 25 batten to perimeter of suspended ceilings | 65 | L,m | 0 | 251.94
E | 25 x 400 board to junction of new and existing suspended ceiling | 1 | ITEM | 0 | 240
F | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_________
|  |  |  | CEILING FINISHES £ | 4604.964
|  |  | TO SUMMARY |  | _________
FITTINGS AND FURNISHINGS
Woodwork and Sundries
Sawn softwood pressure impregnated with preservative and sundries -------------------------------------------------------------------
G | 50 x 50 framing to boxing 300 mm x 300 mm to pipework and wastes and enclose with 12.5 plasterboard and skim coat plaster including angles | 1 | ITEM | 0 | 300
_________
|  |  | To Collection |  | 300
2/14.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
Specialist Fittings
A | Allow the sum of £…… for Counter and shopfitting installations, including changing room; cabinets; shelving and the like to be carried out by a specialist contractor. This may be as a direct contract with the Employer. | 1 | ITEM | 0 | N/a | Omitted as instructed. "Embassy" would be happy to discuss pricing this works if required.
B | Include for enquiries to contractor; liaising with contractor regarding positions, location of services and fixings, including providing builders’ work as required and all making good. | 1 | ITEM | 0 | 487.5
Standard Fittings
C | Jewson’s kitchen base unit 1000 long, Amalfi crystal maple. | 1 | ITEM | 0 | 365.796
D | Jewson’s worktop Tuscan solid wood walnut on 50 x 25 wall
| battens (including cut out for inset sink (sink by others) | 1 | ITEM | 0 | 700.092
Sundries
Wrought softwood rails 150 x 25 chamfered edges and SAA hat and coat hooks at 400 centres (provisional) ------------------------------------------------------------------------
E | 1200 long (1 No) | 1 | Nr | 0 | 57.9
F | 900 long (5 No) | 5 | Nr | 0 | 223.5
G | Include for any other items shown on the drawings or properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_________
|  |  |  | To Collection £ | 1834.788
|  |  |  | Collection | _________
|  |  | 2/14. |  | 300
|  |  | 2/15. |  | 1834.788
_________
|  |  |  | FITTINGS AND £ | 2134.788
|  |  |  | FURNISHINGS | _________
TO SUMMARY
2/15.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
SERVICES
Gutters and Rainwater Pipes
A | 150 Half round uPVC Gutters; and 75 circular rainwater pipes; side rafter; fittings brackets; swan necks; rainwater shoes and the like as indicated | 1 | ITEM | 0 | 568.75
Sanitaryware
B | Include the Sum of £ ………. for the supply of sanitary-ware and sink top. | 1 | ITEM | 0 | 400 | Client supplied Provisional sum
C | Include for Profit and Attendance. | 1 | ITEM | 0 | 60
D | Include for fixing sanitaryware as shown on drawings including assembling wastes, taps, fittings and the like, bedding and sealants. | 1 | ITEM | 0 | 1920
Plumbing and Heating Installation
E | Include the sum of £ ..…… for plumbing and heating installations to be carried out by specialist contractor. | 1 | ITEM | 0 | 6000 | Client supplied Provisional sum
F | Include for Profit and Attendance | 1 | ITEM | 0 | 900
Electrical Installations
G | Include the sum of £……….. for the electrical; fire alarm; and burglar alarm installation to be carried out by specialist contractor | 1 | ITEM | 0 | 15000 | Client supplied Provisional sum (See appendix below for actual quote for works)
H | Include for Profit and Attendance | 1 | ITEM | 0 | 2250
Builders’ Work
I | Make enquiries of services contractors. Include for builders’ work in connection with services, including cutting out and all making good to match existing, removing any debris from site. | 1 | ITEM | 0 | 625
J | Include for any other items shown on the drawings or properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_________
|  |  |  | SERVICES £ | 27723.75
|  |  |  | TO SUMMARY | _________
DECORATIONS
2/16.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
Preparation and Alteration
A | Prepare all existing and new surfaces externally and internally; cut back defective existing areas; make good; bring forward made good areas and prepare for new finishes | 1 | P,sum | 0 | 1020 | P,sum only. A full survey is needed for this item. There are visible signs of rot in certain areas
External
Walls -------
B | Repair to render to rear wall of flat and paint whole wall with three coat Dulux Weathershield | 30 | M2 | 0 | 1233 | Estimated meterage
New and Existing Wood and Metal Surfaces -----------------------------------------------------
Prepare, make good, knott, prime, stop, two undercoats and one gloss coat paint finish to all existing (including existing rear wall of flat) and new work to the following:- ------------------------------------------------------------------------
C | Eaves, verges and the like. | 1 | ITEM | 0 | 702
D | Windows, doors, frames, linings and the like. | 1 | ITEM | 0 | 516
E | Gutters and rainwater pipes to existing. | 1 | ITEM | 0 | 412.8
Internal
Walls and Ceilings -----------------------
Prepare surfaces and decorate in one mist coat and two full coats vinyl silk emulsion to the following:- ------------------------------------------------------------------------
F | Walls to Kitchen | 1 | ITEM | 0 | 150
G | Walls above tiling in Unisex WC | 1 | ITEM | 0 | 60
H | Walls to Lobby and Store | 1 | ITEM | 0 | 258
I | Ceiling to kitchen | 1 | ITEM | 0 | 36
________
|  |  |  | To Collection £ | 4387.8
________
2/17.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
Woodwork and Metalwork -------------- ------------------
Prepare surfaces knot, prime, stop, two undercoats and one gloss coat paint finish to the following:- --------------------------------------------------------------------
A | Windows, doors, linings, architraves and the like | 1 | ITEM | 0 | 441.6
B | Softwood skirtings, hat and coat rails, kitchen batten fittings and the like | 1 | ITEM | 0 | 96
Pipes and Fittings
Pipes and Fittings ---------------------
C | Clean down and prepare, prime, two undercoat and one gloss coat finish. | 1 | ITEM | 0 | 60
D | Include for any other items shown on the drawings or Properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
__________
|  |  | To Collection £ |  | 597.6
|  |  | Collection | ________
|  |  |  | 2/17 | 4387.8
|  |  |  | 2/18 | 597.6
_________
|  |  |  | DECORATIONS £ | 4985.4
|  |  |  | TO SUMMARY | _________
2/18.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
SITEWORKS
Pavings
Remove or prepare existing pavings as required: alter and adapt existing; excavate to reduce level; remove material from site; hardcore 150 thick and lay pavings as shown on plan Appendix E ----------------------------------------------------------------------
A | Tarmacadam paving to area hatched blue | 60 | M2 | 0 | 2100
B | Pavings precast concrete slabs reusing reclaimed and make up shortfall to match to area hatched orange | 24 | M2 | 0 | 540
Composite Work
C | Precast concrete edgings 150 x 50 on foundation and haunching to line as indicated green on plan, including infill behind with gravel | 30 | L,m | 0 | 937.5
D | Screen wall 2.4 high, one brick thick on foundations; brick on edge coping to line as indicated brown on plan | 3 | M2 | 0 | 243.75
E | Line markings; disabled hatching; and disabled symbol | 1 | ITEM | 0 | 475
Sawn softwood treated fencing and gates Chilham “Good Both Sides” as Jackson Fencing 0800 408 2234 ----------------------------------------------------------------------
F | Fencing and posts 1.75 high as shown | 16 | L,m | 0 | 972 | We are unsure where this will be required - so L,m needs confirming.
G | Double gates and posts 1.75 high including fittings | 1 | ITEM | 0 | 625
Landscaping
H | Topsoil to area coloured yellow on plan Appendix E | 6 | M2 | 0 | 37.5
I | Include the sum of £500.00 for soft landscaping | 1 | ITEM | 0 | 500
J | Include for any other items shown on the drawings or properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
|  |  | SITE WORKS £ |  | 6430.75
|  |  |  | TO SUMMARY | ________
2/19.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
DRAINAGE
Preparation/Alteration
A | Include for survey of existing drains and report discrepancies to CA | 1 | ITEM | 0 | 687.5
Excavation and Disposal
Excavate for drains, prepare trenches, backfill above pipes and coverings with selected material, remove subsoil and debris from site, making good existing surfaces -----------------------------------------------------------------------
B | Storm and foul drains as indicated, including locating, re-routing and connecting to existing | 1 | ITEM | 0 | 2012.5
Pipework and Fittings
Supersleeve pipes and fittings 100 mm diameter including polypropylene couplings, bends, junctions, gullies, rodding eyes and the like -----------------------------------------------------------------------
C | Storm drains | 1 | ITEM | 0 | 1125
D | Foul drains | 1 | ITEM | 0 | 1125
E | Connect to existing manhole | 1 | ITEM | 0 | 262.5
F | Soakaways; 5m3 (provisional) | 1 | ITEM | 0 | 312.5
G | Include for soakaway porosity test and report (provisional) | 1 | ITEM | 0 | 250
|  |  |  | To Collection £ | 5775
_______
2/20.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
Beds and Coverings
A | Pea gravel beds and coverings to pipes in paving and landscape areas | 1 | ITEM | 0 | 212.5
B | Plain concrete (1:3:6) beds and coverings to pipes under buildings and car park area | 1 | ITEM | 0 | 550
Manholes/Inspection Chambers
C | Manholes, inspection chambers and covers as indicated | 1 | ITEM | 0 | 631.25
Sundries
D | Test the drains and leave clean and free running on completion. | 1 | ITEM | 0 | 200
E | Provide CCTV survey and video of drains on completion, hand to CA. | 1 | ITEM | 0 | 687.5
F | Include for any other items shown on the drawings or properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
|  |  |  | To Collection £ | 2281.25
_______
Collection
|  |  |  | 2/20. | 5775
|  |  |  | 2/21. | 2281.25
_________
|  |  |  | DRAINAGE £ | 8056.25
|  |  |  | TO SUMMARY | _________
2/21.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
EXTERNAL SERVICES (Provisional)
Preparation
A | Include for scanning for and plotting on drawing existing drains, services and the like, report to CA. | 1 | ITEM | 0 | 250
B | Include the sum of £…….. for diversion or alteration to existing drains and services. | 1 | ITEM | 0 | 1000 | Client supplied Provisional sum
C | Include for any other items shown on the drawings or properly required not specifically scheduled here. | 1 | ITEM | 0 | N/a
_________
EXTERNAL £
|  |  |  | SERVICES TO | 1250
SUMMARY
2/22.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
DAYWORKS
Include the following provisional sums for dayworks to be expended or omitted in part or whole at the instruction of the CA or the Employer ------------------------------------------------------------------
Labour
Include the following hours at the rates to be inserted. Rates are to include all overheads and profit
A | Foreman 10 hours @ £ ………. | 10 | Hrs | 0 | 360
B | Tradesmen 10 hours @ £ ……… | 10 | Hrs | 0 | 300
C | General operatives 10 hours @ £ ……… | 10 | Hrs | 0 | 240
Materials
D | Include the Provisional Sum of £1,000 for materials after deduction of trade discounts. | 1 | ITEM | 0 | 1000
E | Allow for profit and overheads | 1 | ITEM | 0 | 150
Plant
F | Include the Provisional Sum of £500 for plant | 1 | ITEM | 0 | 500
G | Allow for profit and overheads | 1 | ITEM | 0 | 75
CONTINGENCIES
H | Include the contingency sum of £5,000 for unforeseen items to be expended or omitted in part or whole at the instruction of the CA | 1 | ITEM | 0 | 5000
|  |  |  | DAYWORKS AND | ________
|  |  |  | CONTINGENCIES £ | 7625
|  |  |  | TO FINAL | ________
SUMMARY
2/23.
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
SUMMARY OF SCHEDULE OF WORK £
| DEMOLITIONS AND ALTERATIONS .......................................... |  |  |  | 11509.096
| SUBSTRUCTURES .......................................................................... |  |  |  | 22868.75
| EXTERNAL WALLS ........................................................................ |  |  |  | 60712.5
| ROOFS .............................................................................................. |  |  |  | 54261.75
| STAIRS ……………………………………………………………… |  |  |  | 6147.5
| WINDOWS AND EXTERNAL DOORS ......................................... |  |  |  | 1411.56
| INTERNAL WALLS ……………………. ....................................... |  |  |  | 375
| INTERNAL DOORS ………………………….................................. |  |  |  | 1041.408
| WALL FINISHES ............................................................................. |  |  |  | 3549.394
| FLOOR FINISHES .......................................................................... |  |  |  | 12676.992
| CEILING FINISHES ......................................................................... |  |  |  | 4604.964
| FITTINGS AND FURNISHINGS ...................................................... |  |  |  | 2134.788
| SERVICES ......................................................................... ................. |  |  |  | 27723.75
| DECORATIONS ................................................................................. |  |  |  | 4985.4
| SITEWORKS ...................................................................................... |  |  |  | 6430.75
| DRAINAGE ........................................................................................ |  |  |  | 8056.25
| EXTERNAL SERVICES .................................................................. |  |  |  | 1250
| DAYWORK AND CONTINGENCIES ............................................ |  |  |  | 7625
_________
|  |  |  | TO FINAL £ | 237364.852
|  |  |  | SUMMARY | _________
2/24.
FINAL SUMMARY
FINAL SUMMARY
| PRELIMINARIES ……………………………………………….. | 13 | Weeks | 1597.1731 | 20763.25
| SCHEDULE OF WORK ………………………………………… |  |  |  | 237364.852
__________
FINAL
|  |  |  | SUMMARY £ | 258128.102 | Plus VAT
|  |  |  | TO FORM | __________
OF TENDER
APPENDICES
Item | Description | Quantity |  | Rate | £…. | Embassy Comments
Optional Electrical Price Breakdown
Following discussions with the client on site we put forward the proposed items below for the electrical woks
1 | I would recommend that the existing installation be inspected and tested and a Certificate produced before the work commences. | 1 | ITEM | 0 | 300
2 | The installation will require 2 Emergency Exit signs plus 8 emergency lights. | 1 | ITEM | 0 | 840
3 | A fire alarm system, which would consist of a 4-zone panel, 8 smoke detectors, 1 heat detector, 4 break-glass units and 4 sirens | 1 | ITEM | 0 | 1550.4
4 | Removing all old light fittings, sockets etc. | 1 | ITEM | 0 | 600
5 | Moving light switches | 1 | ITEM | 0 | 180
We have not included a cost for the burglar alarm as the existing supplier will have a maintenance contract with the client.
Supplying and installing new lighting, my recommendation is:
6 | Store room: supply only one 28watt 2D fitting; | 1 | ITEM | 0 | 33.6
7 | Rear lobby: supply only low energy, high frequency 2x26watt Downlighter; | 1 | ITEM | 0 | 42
8 | Toilet: supply only low energy, high frequency 2x26watt Downlighter: | 1 | ITEM | 0 | 42
9 | Female Changing Room: Supply only 4 low energy, high frequency 2x26watt Downlighters: | 1 | ITEM | 0 | 168
10 | Male Changing Room: Supply only 2 low energy, high frequency 2x26watt Downlighters: | 1 | ITEM | 0 | 84
11 | Kitchen: Supply one 600x600 high frequency, recessed chrome anti-glare module; | 1 | ITEM | 0 | 36
12 | Counter: Supply only 4 low energy, high frequency 2x26watt Downlighters; Downlighters; | 1 | ITEM | 0 | 168
General lighting:
13 | To achieve a light level of 30watts per sq.metre would require 50 high frequency, adjustable 70watt recessed metal Halides; | 1 | ITEM | 0 | 6084
14 | To wire and install all the above lighting; | 1 | ITEM | 0 | 2760
Window lighting:
15 | 8 adjustable 150watt CDMT high frequency metal Halides; | 1 | ITEM | 0 | 672
16 | To wire and install the above; | 1 | ITEM | 0 | 420
17 | To supply and install additional sockets; | 1 | ITEM | 0 | 576
External lighting:
18 | Lighting on the new stair area and Emergency Lighting at the rear door; | 1 | ITEM | 0 | 420
|  |  |  | Sales Total | 14976